PROJECT KASENA

MVP Architecture & Budget Framework

Preserving Kasem — Powered by Community & Technology

Seed Grant Proposal: GHS 25,000 For Presentation to District Assembly / Member of Parliament

# Executive Summary

Project Kasena is a technology-driven initiative to preserve and digitise the Kasem language spoken by the Kasena-Nankana people of the Upper East Region of Ghana. The project combines a community-powered data collection platform with a structured incentive model to build a world-class Kasem language dataset from the ground up.

Mission: Build the first open, large-scale Kasem language dataset — verified by community elders and powered by youth contributors.

Phase 1 Goal: Collect, verify, and digitise 20,000 high-quality Kasem conversational phrases and vocabulary entries.

Phase 2 (Roadmap): Deploy AI/ML models trained on the dataset to power translation tools, voice assistants, and educational apps.

Seed Funding Request: GHS 25,000 from a District Assembly or Member of Parliament.

# Part 1: Technical Architecture (MVP Phase)

The MVP is designed as a lightweight, scalable system that prioritises data collection over complex AI processing. The architecture is deliberately lean — minimising infrastructure costs while building a foundation that is ready for AI integration in Phase 2.

## 1.1  Frontend — The User Interface

Framework: Next.js (React) or Flutter

Next.js is the recommended choice for the following reasons:

- Progressive Web App (PWA) capability: Users can install the platform on their smartphones directly from the browser — no app store required. This removes a significant barrier to adoption in areas where users may have limited mobile data or older devices.

- Offline-first potential: PWA technology enables data caching, meaning contributors in low-connectivity areas (e.g. rural Navrongo) can use the app offline and sync when a connection is available — critical for the target geography.

- Ecosystem maturity: Next.js has a large developer community, extensive documentation, and excellent free hosting options, reducing long-term maintenance costs.

Styling: Tailwind CSS — a utility-first framework that enables rapid, consistent, and mobile-responsive UI development with minimal custom code.

## 1.2  Backend — The Logic & API

Framework: Python with FastAPI

Python was selected as the backend language for a strategic reason:

- AI-native ecosystem: Python is the primary language for machine learning and natural language processing (NLP). By building the backend in Python from Day 1, the infrastructure aligns perfectly with the Phase 2 AI roadmap — plugging in ML models will require minimal refactoring.

- FastAPI performance: FastAPI is one of the fastest Python web frameworks available, providing automatic API documentation (OpenAPI/Swagger), asynchronous request handling, and built-in data validation — all important for a high-volume data ingestion platform.

- Developer availability: Python developers are widely available, reducing hiring costs and dependency on specialist talent.

## 1.3  Database — The Vault

Primary Database: PostgreSQL (via Supabase)

Supabase was selected as the database solution for several operational advantages:

- Backend-as-a-Service: Supabase provides instant database hosting, a built-in REST API, and real-time capabilities — dramatically reducing backend setup time and cost.

- User authentication out of the box: Students and contributors can register, log in, and be tracked for bounty payouts without building a custom auth system. Social logins (Google, phone OTP) are supported natively.

- Relational data model: Kasem language data is inherently relational. The database schema can cleanly model: Word → English Translation → Kasem Translation → Contributor ID → Validator Status → Payout Flag.

- Scalability: Supabase runs on PostgreSQL, one of the world's most reliable and scalable open-source databases. It can grow from 0 to millions of records without a platform migration.

## 1.4  Hosting & Infrastructure

| Component | Details |
| --- | --- |
| Frontend Hosting | Vercel — Free tier is exceptionally generous for Next.js applications. Includes global CDN, automatic HTTPS, and CI/CD deployment from GitHub. |
| Backend / Database | Supabase — Free tier sufficient for MVP. Paid plans start at ~$25/month and scale with usage. No DevOps overhead required. |
| Domain | kasena-ai.org or kasena.app — Approx. GHS 100–150/year for registration. |
| SMS / OTP | Africa's Talking or Hubtel SMS Gateway — Pay-per-SMS model for user verification. Estimated GHS 200–400/month at scale. |
| MVP Cost Estimate | Infrastructure costs during the MVP phase are projected to be near zero. Significant costs will only arise when the platform exceeds tens of thousands of active daily users. |

# Part 2: "Data Bounty" Budget Framework

This section provides a detailed justification for the GHS 25,000 seed grant request. The budget is structured around four pillars, each with a clear mechanism, a defined payout logic, and measurable outputs.

Primary Objective: Collect, verify, and digitise 20,000 high-quality Kasem conversational phrases and vocabulary entries within the MVP phase.

Funding Source: District Assembly Grant or MP Constituency Development Fund.

Accountability: All transactions to be tracked on-platform with exportable reports for transparency.

## Pillar 1: Youth Contributors — The Crowd

Allocated Budget: GHS 10,000  |  40% of Total

Mechanism: University and SHS students submit Kasem phrases, sentences, and vocabulary entries through the mobile app.

Payout Rate: GHS 0.50 per verified phrase or sentence.

Target Volume: 20,000 verified submissions from the contributor pool.

Why this model works:

- Gamification drives volume: The bounty model transforms language preservation into an income opportunity. A student at CKT-UTAS who submits 100 quality phrases earns GHS 50 — enough for a week of mobile data and meals. This is a meaningful incentive in the local economic context.

- Quality gates prevent gaming: Submissions are only paid upon successful validation by an Elder/Teacher Validator (see Pillar 2). Contributors are incentivised to submit accurate, high-quality content, as low-quality submissions will be rejected and unpaid.

- Scalable leaderboard: Top contributors are featured on a public leaderboard within the app, creating social recognition and healthy competition that drives organic participation beyond monetary rewards.

- Demographic reach: Targeting students at CKT-UTAS, Navrongo SHS, Notre Dame SHS, and other Upper East institutions ensures a wide, diverse contributor base that reflects natural Kasem language variation across age groups and sub-dialects.

## Pillar 2: Elder & Teacher Validators — The Gatekeepers

Allocated Budget: GHS 8,000  |  32% of Total

Mechanism: 3–4 respected Kasem teachers or community elders serve as platform Administrators, reviewing and approving or rejecting youth submissions.

Payout Structure: Monthly stipend of GHS 1,000 per validator, for 2 months (4 validators x GHS 1,000 x 2 months = GHS 8,000).

Why validators are non-negotiable:

- Raw internet data is unreliable: Kasem is an oral language with no standardised digital corpus. Crowdsourced data without expert review will contain errors, code-switching (Kasem-English mixing), and culturally inappropriate content that would corrupt the dataset permanently.

- Cultural authority: Elder validators ensure that proverbs, idioms, and context-specific phrases are recorded with their correct cultural meaning and usage — something a purely algorithmic quality check cannot achieve.

- Academic integrity: A validated dataset has credibility with universities, research institutions, and international language preservation bodies (e.g. UNESCO, SIL International), opening doors for future grant funding and academic partnerships.

- Two-stage validation: The system is designed with a two-stage process — an initial automated check (spelling, length, language detection) followed by human expert review — to reduce the burden on validators while maintaining quality.

## Pillar 3: Community Mobilisation & Data Drives

Allocated Budget: GHS 4,000  |  16% of Total

Mechanism: Structured launch events and Data Drive campaigns at secondary schools and community centres across the Kasena-Nankana area.

Target venues for Data Drives:

- Navrongo Senior High School (Navrongo SHS)

- Notre Dame Girls' Senior High School

- CKT-UTAS Navrongo Campus

- Community centres in Paga, Chuchuliga, and Sandema

Budget breakdown for mobilisation:

- Transport & logistics: GHS 1,500 — Vehicle hire for organisers, fuel, and on-ground coordination across multiple school visits.

- Radio campaign (Nabiina Radio & Radio Upper East): GHS 1,000 — Targeted broadcast announcements in Kasem and English explaining the project, bounty payouts, and how to participate. Radio remains the highest-reach medium in the Upper East Region.

- Physical incentives: GHS 1,000 — Branded T-shirts, certificates, and small prizes for top contributors at each launch event. Physical recognition items have high perceived value and serve as walking advertisements for the project.

- Print materials: GHS 500 — Posters, flyers, and how-to guides (in Kasem and English) for distribution at schools, churches, and markets.

## Pillar 4: Technology Operations & Contingency

Allocated Budget: GHS 3,000  |  12% of Total

This pillar covers essential operational technology costs and provides a buffer for unforeseen expenses.

Breakdown:

- Domain registration: GHS 150 — Annual registration of kasena-ai.org or kasena.app to establish a permanent online identity for the project.

- SMS gateway / OTP verification: GHS 400 — Integration with Africa's Talking or Hubtel to send one-time passwords (OTPs) to new users upon registration. Mobile number verification is essential for preventing duplicate accounts and ensuring bounty payouts go to real individuals.

- Paid infrastructure upgrade buffer: GHS 500 — If the MVP grows faster than projected and exceeds free-tier limits on Supabase or Vercel, this covers the first 1–2 months of paid hosting.

- Contingency reserve: GHS 1,950 — A 7.8% contingency buffer for unforeseen costs, delays, or opportunities (e.g. a spontaneous partnership event, emergency transport, or additional validator stipend).

# Budget Summary

| Budget Line Item | Amount (GHS) | % of Total |
| --- | --- | --- |
| Pillar 1: Youth Contributors (Data Bounties @ GHS 0.50/phrase) | GHS 10,000 | 40% |
| Pillar 2: Elder & Teacher Validators (4 x GHS 1,000 x 2 months) | GHS 8,000 | 32% |
| Pillar 3: Community Mobilisation & Data Drive Events | GHS 4,000 | 16% |
| Pillar 4: Tech Ops, Domain, SMS Gateway & Contingency | GHS 3,000 | 12% |
| TOTAL SEED REQUEST | GHS 25,000 | 100% |

# Success Metrics & Expected Outcomes

The following measurable outcomes are expected upon completion of the MVP phase:

| Component | Details |
| --- | --- |
| Dataset Size | 20,000+ verified Kasem phrases, sentences, and vocabulary entries |
| Contributor Base | 200–500 active youth contributors registered on the platform |
| Validator Network | 3–4 certified Elder/Teacher Validators with documented review history |
| Community Reach | 5+ schools and community groups engaged through Data Drive events |
| Platform Status | Fully functional web/PWA application, live and publicly accessible |
| Phase 2 Readiness | Dataset sufficient to begin training a baseline Kasem NLP/translation model |

# Phase 2 Roadmap (Post-MVP)

Successful delivery of the MVP and this seed grant will position Project Kasena to pursue the following in Phase 2:

- AI Model Training: Use the verified 20,000-entry dataset to fine-tune an open-source language model (e.g. Meta's mBART or NLLB) for Kasem-English translation.

- Voice & Audio Integration: Add audio recording to the platform so contributors can record spoken Kasem, building a corpus for speech recognition and text-to-speech (TTS) models.

- Educational App: Deploy a standalone Kasem language learning app for schools, targeting Kasem literacy in early primary education.

- Institutional Partnerships: Engage CKT-UTAS, University of Ghana, and international bodies (UNESCO, SIL) for research collaboration and follow-on grant funding.

- Expanded Funding: Leverage the MVP evidence base to apply for larger grants from the Ghana Innovation Fund, Google.org, or the African Development Bank's digital inclusion programmes.

Every language lost is a world gone silent.

Project Kasena is a community's act of remembrance — and a nation's investment in its own future.